## v37
目標 | 問題 | 原因 | 對策
音頻質量保證 | ACM處有邏輯不通情況發生 | rtp/rtcp協議數據與邏輯結合造成 | A：幹掉RTP協議 B：加入RTP
清晰易用的接口 | codec數據庫混亂 | 裁剪數據庫不一致造成 | A：修改DB到一致 B：加入偽CODEC
魯棒系統，無具有依賴關係的api | 兩個codec未經過測試 | 時間不夠 | 時間允許或者下一階段 做一個測試接口數據程序驗證
一個測試和驗證的工具 | neteq未讀通 | 缺乏了解 | A：讀懂代碼 B：找個方法幹掉代碼
一個完整無依賴的發布程序包 | 整條路徑未通導致不能隨意裁剪 | codec和neteq RTP未全了解 | 讀懂ACM代碼 讀懂NETEQ代碼 讀懂RTP協議 讀懂RTP代碼
| 數據包大小以及數據未經過測試 | 缺乏紮實的知識，沒時間 | 各個節點提供工具 讀懂基礎音頻知識
| 引擎開關定義需完善 | 前期變動較大 | 固定開關接口
TODO |  | 優先 | 時間
閱讀 | RTP協議 | 1 | 3
| PCM編碼 | 3 | 2
| OPUS編碼 | 3 | 2
| 編碼器原理 | 1 | 1
| neteq原理 | 3 | 2
| 數字音頻基礎知識 | 2 | 1
| RTP模塊代碼 | 3 | 4
| NETEQ模塊代碼 | 3 | 5
| ACM模塊代碼 | 2 | 2
| 引擎數據流向框架代碼 | 1 | 3
| opus接口 | 4 | 2
| pcm接口 | 4 | 2
工作 | 融合ACM2 | 2 | 5
| 融合NETEQ4 | 2 | 5
| 融合RTP代碼 | 2 | 10
| 去掉無用模塊 | 2 | 6 | 26
| 整理接口代碼 | 1 | 4
| 測試各個模塊工作狀態工具（待定） | 3
| 去掉RTP邏輯 | 2 | 4
| 去掉NETEQ | 2 | 6
| 去掉RTP在編碼解碼的邏輯 | 2 | 6
| 讀懂流程後將接口中間的不需要部分幹掉 |  | 5 | 21
| 跟踪音頻基本數據 | 5 | 10
| 跟踪引擎處理的數據 MICLEVE etc | 5 | 10
| 測試並修復bug | 3 | 20
120
Note on A29: 东东:

## audio engine todo
发行版本
debug | mtd | mdd
release | mt | md
瘦身
制定一个第三方代码库管理方案
裁剪代码 | codec
开关
测试 | 回环测试
UDP测试
原先代码测试

## macros
cpu | WEBRTC_ARCH_ARM
WEBRTC_ARCH_ARM_NEON
WEBRTC_ARCH_ARM_V7
WEBRTC_DETECT_ARM_NEON
WEBRTC_ARCH_BIG_ENDIAN
browser | WEBRTC_MOZILLA_BUILD
supported functions | WEBRTC_VOE_EXTERNAL_REC_AND_PLAYOUT
WEBRTC_VOICE_ENGINE_AGC
WEBRTC_VOICE_ENGINE_ECHO
WEBRTC_VOICE_ENGINE_NR
WEBRTC_VOICE_ENGINE_TYPING_DETECTION
WEBRTC_DTMF_DETECTION
os | WEBRTC_ANDROID
WEBRTC_ANDROID_OPENSLES
WEBRTC_ANDROID_PLATFORM_BUILD
WEBRTC_IOS
WEBRTC_LINUX
WEBRTC_MAC
WEBRTC_WINDOWS_CORE_AUDIO_BUILD
debug | WEBRTC_AEC_DEBUG_DUMP
WEBRTC_AUDIOPROC_DEBUG_DUMP
WEBRTC_DIRECT_TRACE
codec | WEBRTC_CODEC_AMR
WEBRTC_CODEC_AMRWB
WEBRTC_CODEC_AVT
WEBRTC_CODEC_CELT
WEBRTC_CODEC_G722
WEBRTC_CODEC_G722_1
WEBRTC_CODEC_G722_1C
WEBRTC_CODEC_G726
WEBRTC_CODEC_G729
WEBRTC_CODEC_G729_1
WEBRTC_CODEC_GSMFR
WEBRTC_CODEC_ILBC
WEBRTC_CODEC_ISAC
WEBRTC_CODEC_ISACFX
WEBRTC_CODEC_ISACLC
WEBRTC_CODEC_OPUS
WEBRTC_CODEC_PCM16
WEBRTC_CODEC_RED
engine switch | WEBRTC_VOICE_ENGINE_AUDIO_PROCESSING_API
WEBRTC_VOICE_ENGINE_CODEC_API
WEBRTC_VOICE_ENGINE_DTMF_API
WEBRTC_VOICE_ENGINE_EXTERNAL_MEDIA_API
WEBRTC_VOICE_ENGINE_FILE_API
WEBRTC_VOICE_ENGINE_HARDWARE_API
WEBRTC_VOICE_ENGINE_NETEQ_STATS_API
WEBRTC_VOICE_ENGINE_VIDEO_SYNC_API
WEBRTC_VOICE_ENGINE_VOLUME_CONTROL_API
WEBRTC_VOICE_ENGINE_RTP_RTCP_API
system support | WEBRTC_CLOCK_TYPE_REALTIME
WEBRTC_NO_STL
WEBRTC_THREAD_RR
WEBRTC_EXPORT
optional functions | WEBRTC_MODULE_UTILITY_VIDEO
WEBRTC_NETEQ_40BITACC_TEST
WEBRTC_DUMMY_RTP
WEBRTC_EXTERNAL_TRANSPORT
WEBRTC_ISAC_FIX_NB_CALLS_ENABLED

## wavesheet
type | name | samplerate freq | bit | channel | bit rate | packetsize
|  | 8000 | 4 | 1 | 32000 | 80 | a u pcm | 8000 | 8 | 64000
0/8 | pcmu/pcma | 8000 | 8 | 1 | 64000 | 160 | pcm | 8000 | 16 | 128000
107 | L16 | 8000 | 16 | 1 | 128000 | 80 | adpcm | 8000 | 4 | 32000 | 60/120
[7 empty] | adpcm | 6000 | 4 | 24000

## Sheet3
Payload type (PT) | Name | Type | No. of channels | Clock rate (Hz) | Frame size (ms)
0 | PCMU | audio | 1 | 8000 | any
4 | G723 | audio | 1 | 8000 | 30
5 | DVI4 | audio | 1 | 8000 | any
6 | DVI4 | audio | 1 | 16000 | any
7 | LPC | audio | 1 | 8000 | any
8 | PCMA | audio | 1 | 8000 | any
9 | G722 | audio | 1 | 8000 | any
10 | L16 | audio | 2 | 44100 | any
11 | L16 | audio | 1 | 44100 | any
12 | QCELP | audio | 1 | 8000 | 20
13 | CN | audio | 1 | 8000
14 | MPA | audio | 1 | 90000
15 | G728 | audio | 1 | 8000 | 2.5
16 | DVI4 | audio | 1 | 11025 | any
17 | DVI4 | audio | 1 | 22050 | any
18 | G729 | audio | 1 | 8000 | 10
33 | MP2T | audio/video | 1 | 90000
34 | H263 | video |  | 90000
35 - 71 | unassigned
72 - 76 | Reserved for RTCP conflict avoidance | N/A |  | N/A
77 - 95 | unassigned
dynamic | iLBC | audio | 1 | 8000 | 20 or 30
dynamic | PCMA-WB | audio |  | 16000 | 5
dynamic | PCMU-WB | audio |  | 16000 | 5
dynamic | G718 | audio |  | 32000 (placeholder) | 20
dynamic | G719 | audio | (various) | 48000 | 20
dynamic | G7221 | audio |  | 32000, 16000 | 20
dynamic | G726-16 | audio | 1 | 8000 | any
dynamic | G726-24 | audio | 1 | 8000 | any
dynamic | G726-32 | audio | 1 | 8000 | any
dynamic | G726-40 | audio | 1 | 8000 | any
dynamic | G729D | audio | 1 | 8000 | 10
dynamic | G729E | audio | 1 | 8000 | 10
dynamic | G7291 | audio |  | 16000 | 20
dynamic | GSM-EFR | audio | 1 | 8000 | 20
dynamic | GSM-HR-08 | audio | 1 | 8000 | 20
dynamic (or profile) | AMR | audio | (various) | 8000 | 20
dynamic (or profile) | AMR-WB | audio | (various) | 16000 | 20
dynamic (or profile) | AMR-WB+ | audio | 1, 2 or omit | 72000 | 80 (super-frame; internally divided in to transport frames of 13.33, 14.22, 15, 16, 17.78, 20, 21.33, 24, 26.67, 30, 35.55, or 40)
dynamic (or profile) | vorbis | audio | (various) | any (must be a multiple of sample rate)
dynamic (or profile) | opus | audio | 1, 2 | 48000 | 2.5, 5, 10, 20, 40, or 60
dynamic (or profile) | speex | audio | 1 | 8000, 16000 or 32000 | 20
dynamic (96-127) | mpa-robust | audio |  | 90000
dynamic (or profile) | MP4A-LATM | audio |  | 90000 or others
dynamic (or profile) | MP4V-ES | video |  | 90000 or others
dynamic (or profile) | mpeg4-generic | audio/video |  | 90000 or other
dynamic | VP8 | video |  | 90000
dynamic | L8 | audio | (various) | (various) | any
dynamic | DAT12 | audio | (various) | 8000, 11025, 16000, 22050, 24000, 32000, 44100, 48000 or others | any
dynamic | L16 | audio | (various) | 8000, 11025, 16000, 22050, 24000, 32000, 44100, 48000 or others | any
dynamic | L20 | audio | (various) | 8000, 11025, 16000, 22050, 24000, 32000, 44100, 48000 or others | any
dynamic | L24 | audio | (various) | 8000, 11025, 16000, 22050, 24000, 32000, 44100, 48000 or others | any

## profile
RTP/AVP audio and video payload types
Payload type (PT) | Name | Type | No. of channels | Clock rate (Hz) | Frame size (ms) | Default packet size (ms) | Description | References
0 | PCMU | audio | 1 | 8000 | any | 20 | ITU-T G.711 PCM µ-Law Audio 64 kbit/s | RFC 3551
1 | reserved (previously 1016) | audio | 1 | 8000 |  |  | reserved, previously CELP Audio 4.8 kbit/s | RFC 3551, previously RFC 1890
2 | reserved (previously G721) | audio | 1 | 8000 |  |  | reserved, previously ITU-T G.721 ADPCM Audio 32 kbit/s | RFC 3551, previously RFC 1890
3 | GSM | audio | 1 | 8000 | 20 | 20 | European GSM Full Rate Audio 13 kbit/s (GSM 06.10) | RFC 3551
4 | G723 | audio | 1 | 8000 | 30 | 30 | ITU-T G.723.1 | RFC 3551
5 | DVI4 | audio | 1 | 8000 | any | 20 | IMA ADPCM Audio 32 kbit/s | RFC 3551
6 | DVI4 | audio | 1 | 16000 | any | 20 | IMA ADPCM 64 kbit/s | RFC 3551
7 | LPC | audio | 1 | 8000 | any | 20 | Experimental Linear Predictive Coding Audio | RFC 3551
8 | PCMA | audio | 1 | 8000 | any | 20 | ITU-T G.711 PCM A-Law Audio 64 kbit/s | RFC 3551
9 | G722 | audio | 1 | 8000 | any | 20 | ITU-T G.722 Audio | RFC 3551 - Page 14
10 | L16 | audio | 2 | 44100 | any | 20 | Linear PCM 16-bit Stereo Audio 1411.2 kbit/s,[2][3][4] uncompressed | RFC 3551, Page 27
11 | L16 | audio | 1 | 44100 | any | 20 | Linear PCM 16-bit Audio 705.6 kbit/s, uncompressed | RFC 3551, Page 27
12 | QCELP | audio | 1 | 8000 | 20 | 20 | Qualcomm Code Excited Linear Prediction | RFC 2658, RFC 3551
13 | CN | audio | 1 | 8000 |  |  | Comfort noise. Payload type used with audio codecs that do not support comfort noise as part of the codec itself such as G.711, G.722.1, G.722, G.726, G.727, G.728, GSM 06.10, Siren, and RTAudio. | RFC 3389
14 | MPA | audio | 1 | 90000 |  |  | MPEG-1 or MPEG-2 Audio Only | RFC 3551, RFC 2250
15 | G728 | audio | 1 | 8000 | 2.5 | 20 | ITU-T G.728 Audio 16 kbit/s | RFC 3551
16 | DVI4 | audio | 1 | 11025 | any | 20 | IMA ADPCM | RFC 3551
17 | DVI4 | audio | 1 | 22050 | any | 20 | IMA ADPCM | RFC 3551
18 | G729 | audio | 1 | 8000 | 10 | 20 | ITU-T G.729 and G.729a | RFC 3551, Page 20
25 | CELB | video | 1 | 90000 |  |  | Sun's CellB Video Encoding[5] | RFC 2029
26 | JPEG | video | 1 | 90000 |  |  | JPEG Video | RFC 2435
28 | NV | video | 1 | 90000 |  |  | Xerox PARC's Network Video (nv)[6] | RFC 3551, Page 32
31 | H261 | video | 1 | 90000 |  |  | ITU-T H.261 Video | RFC 4587
32 | MPV | video | 1 | 90000 |  |  | MPEG-1 and MPEG-2 Video | RFC 2250
33 | MP2T | audio/video | 1 | 90000 |  |  | MPEG-2 transport stream Video | RFC 2250
34 | H263 | video |  | 90000 |  |  | H.263 video, first version (1996) | RFC 3551, RFC 2190
35 - 71 | unassigned | [6 empty] | RFC 3551, Page 32
72 - 76 | Reserved for RTCP conflict avoidance | N/A |  | N/A |  |  |  | RFC 3551, Page 32
77 - 95 | unassigned | [6 empty] | RFC 3551, Page 32
dynamic | H263-1998 | video |  | 90000 |  |  | H.263 video, second version (1998) | RFC 3551, RFC 4629, RFC 2190
dynamic | H263-2000 | video |  | 90000 |  |  | H.263 video, third version (2000) | RFC 4629
dynamic (or profile) | H264 | video |  | 90000 |  |  | H.264 video (MPEG-4 Part 10) | RFC 6184, previously RFC 3984
dynamic (or profile) | theora | video |  | 90000 |  |  | Theora video | draft-barbato-avt-rtp-theora-01
dynamic | iLBC | audio | 1 | 8000 | 20 or 30 | 20 or 30, respectively | Internet low Bitrate Codec 13.33 or 15.2 kbit/s | RFC 3952
dynamic | PCMA-WB | audio |  | 16000 | 5 |  | ITU-T G.711.1, A-law | RFC 5391
dynamic | PCMU-WB | audio |  | 16000 | 5 |  | ITU-T G.711.1, µ-law | RFC 5391
dynamic | G718 | audio |  | 32000 (placeholder) | 20 |  | ITU-T G.718 | draft-ietf-avt-rtp-g718-03
dynamic | G719 | audio | (various) | 48000 | 20 |  | ITU-T G.719 | RFC 5404
dynamic | G7221 | audio |  | 32000, 16000 | 20 |  | ITU-T G.722.1 | RFC 5577
dynamic | G726-16 | audio | 1 | 8000 | any | 20 | ITU-T G.726 audio with 16 kbit/s | RFC 3551
dynamic | G726-24 | audio | 1 | 8000 | any | 20 | ITU-T G.726 audio with 24 kbit/s | RFC 3551
dynamic | G726-32 | audio | 1 | 8000 | any | 20 | ITU-T G.726 audio with 32 kbit/s | RFC 3551
dynamic | G726-40 | audio | 1 | 8000 | any | 20 | ITU-T G.726 audio with 40 kbit/s | RFC 3551
dynamic | G729D | audio | 1 | 8000 | 10 | 20 | ITU-T G.729 Annex D | RFC 3551
dynamic | G729E | audio | 1 | 8000 | 10 | 20 | ITU-T G.729 Annex E | RFC 3551
dynamic | G7291 | audio |  | 16000 | 20 |  | ITU-T G.729.1 | RFC 4749
dynamic | GSM-EFR | audio | 1 | 8000 | 20 | 20 | ITU-T GSM-EFR (GSM 06.60) | RFC 3551
dynamic | GSM-HR-08 | audio | 1 | 8000 | 20 |  | ITU-T GSM-HR (GSM 06.20) | RFC 5993
dynamic (or profile) | AMR | audio | (various) | 8000 | 20 |  | Adaptive Multi-Rate audio | RFC 4867
dynamic (or profile) | AMR-WB | audio | (various) | 16000 | 20 |  | Adaptive Multi-Rate Wideband audio (ITU-T G.722.2) | RFC 4867
dynamic (or profile) | AMR-WB+ | audio | 1, 2 or omit | 72000 | 80 (super-frame; internally divided in to transport frames of 13.33, 14.22, 15, 16, 17.78, 20, 21.33, 24, 26.67, 30, 35.55, or 40) |  | Extended Adaptive Multi Rate – WideBand audio | RFC 4352
dynamic (or profile) | vorbis | audio | (various) | any (must be a multiple of sample rate) |  | as many Vorbis packets as fit within the path MTU, unless it exceeds an application's desired transmission latency | RTP Payload Format for Vorbis Encoded Audio | RFC 5215
dynamic (or profile) | opus | audio | 1, 2 | 48000 | 2.5, 5, 10, 20, 40, or 60 | 20, minimum allowed value 3 (rounded from 2.5), maximum allowed value 120 (allowed values are 3, 5, 10, 20, 40, or 60 or an arbitrary multiple of Opus frame sizes rounded up to the next full integer value up to a maximum value of 120) | RTP Payload Format for Opus Speech and Audio Codec | draft
dynamic (or profile) | speex | audio | 1 | 8000, 16000 or 32000 | 20 |  | RTP Payload Format for the Speex Codec | RFC 5574
dynamic (96-127) | mpa-robust | audio |  | 90000 |  |  | A More Loss-Tolerant RTP Payload Format for MP3 Audio | RFC 5219
dynamic (or profile) | MP4A-LATM | audio |  | 90000 or others |  | recommended same as frame size | RTP Payload Format for MPEG-4 Audio | RFC 6416 (previously RFC 3016)
dynamic (or profile) | MP4V-ES | video |  | 90000 or others |  | recommended same as frame size | RTP Payload Format for MPEG-4 Visual | RFC 6416 (previously RFC 3016)
dynamic (or profile) | mpeg4-generic | audio/video |  | 90000 or other |  |  | RTP Payload Format for Transport of MPEG-4 Elementary Streams | RFC 3640
dynamic | VP8 | video |  | 90000 |  |  | RTP Payload Format for Transport of VP8 Streams | draft-ietf-payload-vp8-08
dynamic | L8 | audio | (various) | (various) | any | 20 | Linear PCM 8-bit audio with 128 offset | RFC 3551 Section 4.5.10 and Table 5
dynamic | DAT12 | audio | (various) | 8000, 11025, 16000, 22050, 24000, 32000, 44100, 48000 or others | any | 20 (by analogy with L16) | IEC 61119 12-bit nonlinear audio | RFC 3190 Section 3
dynamic | L16 | audio | (various) | 8000, 11025, 16000, 22050, 24000, 32000, 44100, 48000 or others | any | 20 | Linear PCM 16-bit audio | RFC 3551 Section 4.5.11, RFC 2586
dynamic | L20 | audio | (various) | 8000, 11025, 16000, 22050, 24000, 32000, 44100, 48000 or others | any | 20 (by analogy with L16) | Linear PCM 20-bit audio | RFC 3190 Section 4
dynamic | L24 | audio | (various) | 8000, 11025, 16000, 22050, 24000, 32000, 44100, 48000 or others | any | 20 (by analogy with L16) | Linear PCM 24-bit audio | RFC 3190 Section 4